## First Draft
Task | Type | Section | Jacob Flag | Estimated Duration | Actual duration | Date of completion
Collect important references on model calibration tools (Abaqus/others?) | References | Intro |  | 2:00
Paragraphs describing the pre-processor (filtering/plotting/data selection) | Content | Methods | JACOB | 3:00
A few paragraphs on the post-processor. What do we do with the data? (We haven't really talked about this before). | Content | Methods | JACOB | 1:30
Set of figures describing the full manual calibration process. Strain-temperature (a), E^A (b), TTs and Cs ©, trans. Strain (d). Include alpha in (a) and ©. | Figure | Methods |  | 2:00 | 3:00 | 2024-05-14 | Got it drafted on paper. Move to inkscape now. Maybe play with the aspect ratios to get everything down.
Add a table with the two calibration parameters.
What is SMA constitutive model calibration? (paragraph) | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
Why is model calibration important? (paragraph) | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
What is the current state-of-the-art for model calibration? (paragraph) | Content | Intro |  | 2:00 | 0:15 |  | Word dump complete.
Any drawbacks to the current state-of-the-art? (paragraph) | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
Figure describing the full design process (property definition -> alloy development -> alloy fabrication <-> property determination -> model calibration -> design with component) and how our tool speeds this process up. | Figure | Intro | JACOB? | 3:00 | 2:30 |  | Mostly done. Just need to fine-tune it.
Figures justifying the need for numerical optimization. Pull from the SMASIS slide deck. | Figure | Intro |  | 1:00 | 1:30 | 2023-11-05 | I have a handful of figures, but probably need to clean these up and trim them down.
Flowchart describing the different components of the tool (pull from SMASIS slides). | Figure | Methods | JACOB | 1:30 | 1:00 |  | Mostly there. Just fine tuning.
Justify the use of the 1D Lagoudas SMA actuator model. (applicability to more complex systems, dearth of tools on that area, etc.) | Content | Methods |  | 1:00
Briefly describe the 1D Lagoudas SMA model (write out all the equations). Probably re-write it in terms of an elastic domain, yield critierion, and flow rule. | Content | Methods |  | 2:00
Describe optimization scheme (hybrid optimization) | Content | Methods |  | 1:00 | 0:45 | 2023-11-06 | Word dump complete.
3 paragraphs on conclusions (open source, speed of development, other applications) | Content | Conclusion |  | 1:00 | 0:15 | 2024-04-23 | Word dump complete.
2 paragraphs on further refinements (alternative loading modes, model formulations, anything else?) | Content | Conclusion |  | 1:00 | 0:05 | 2024-04-23 | Word dump complete.
Figure detailing difference between hybrid optimization, GA, and gradient-based methods. | Figure | Methods |  | 2:00 |  |  | Probably don't need this figure. It's not an optimization paper - it's a model calibration GUI paper.
Write the thesis statement paragraph | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
Collect 5-10 references on SMA model calibration | References | Intro |  | 2:00 | 1:50 | 2023-09-20
Collect the important references on existing open-source tools for SMAs (NASA). | References | Intro |  | 2:00 | 2:30 | 2023-09-23
Table of unknown parameters (design variables), their physical meanings, and SI units. | Table | Methods |  | 2:00 | 0:30 | 2023-10-03
Figure outlining calibration progress (4 subfigures showing convergence to the true solution?) | Figure | Example |  | 1:00 | 3:00 | 2024-02-27 | I have a table to go through this. Showing the analytical solution then moving to the optimized solution.
Percent Complete |  |  |  | 72.73%
Total Time Elapsed |  |  |  | 1899-12-31 11:00 | 0.75694

## Second Draft
Task | Type | Section | Talk to Jacob? | Estimated Duration | Actual duration | Date of completion | Notes
Clean up the "current tools" paragraph | Content | Intro |  | 1:00
Should we change "preprocessing" to "processing" to take a less model-centric perspective? | Figures/Org | Intro | Yes | 0:25
Think about organization with figure 2 (SMA-REACT description). Does this belong in its own section? | Organization | Intro |  | 0:25
Add a sentence or two about our intended audience for the paper (we write this paper for…). That allows us to scope the mathematical details of the paper. | Content | Intro | Yes | 0:25 |  |  | From that scoping, I'll know how much detail we'll need to provide on the Lagoudas constitutive model.
In the SMA development process, do we need to introduce roles and personas for each person doing a different stage of the work? | Content | Intro + Methods | Yes | 0:30 | 0:15 | 2024-08-29 | If we introduce different personas and decide on titles, that'll make explaining the model calibration part much easier. Nope.
Paragraphs describing the pre-processor (filtering/plotting/data selection) | Content | Methods | Yes | 3:00
A few paragraphs on the post-processor. What do we do with the data? (We haven't really talked about this before). | Content | Methods | Yes | 1:30
Consider deleting first paragraph in model calibration | Content | Methods |  | 0:45 |  |  | Just read through to make sure it flows.
2nd paragraph in model calibration: Move the last sentence to be the topic sentence. | Content | Methods |  | 0:30 |  |  | Make sure it flows and make sure I'm not saying the same thing twice.
Collect references on analytical calibration methods for SMAs | References | Methods |  | 0:45
Model calibration, paragraph 5: Have I mentioned material property interdependence before now? | Content | Methods |  | 0:45
Methods -> 1D Constitutive Model: Is this section a primer on SMAs constitutive models, or on how you need numerical optimization for calibration? | Content | Methods |  | 0:30
Do I need to divide model parameters into free variables and specified quantities? | Content | Methods |  | 0:30
Ask Jacob to see if we can get a preprint of the SMA book chapter on calibration. | Organization | Methods | Yes | 0:10
Get a citation for how to select the calibration stress | References | Methods |  | 0:15
Get a citation for how in most cases the H_min and sigma_crit are zero. | References | Methods |  | 0:25 |  |  | Just look through the book or other examples. This makes sense, because you'll either get grain realignment or you won't…
The statement about how the ASTM standard defines properties in a different manner than the Lagoudas model is buried in a paragraph. Pull that out. | Content | Methods |  | 0:15 |  |  | Maybe move this up to a section about why we need a separate calibration tool.
"In past work,…" move this to a more relevant section. Maybe to the introduction? Maybe cut it in general? | Content | Methods |  | 0:20
Check the entire model description section for any mathematical rationale that doesn't have the accompanying math. | Content | Methods |  | 0:45
Change iterative calibration/conventional calibration to sequential? Because both are iterative. | Content | Methods | Yes | 0:30 |  |  | Figure out something that Jacob can understand.
Look through the ASTM standard to pull a quick discussion about what stress levels to pick out. | Content | Methods |  | 0:30 |  |  | Keep it succint. This isn't an SMA characterization paper.
Make the conventional/sequential calibration figures better aspect ratios. | Figures | Methods |  | 0:25
Add the data for the bounds on the concurrent/global calibration section | Content | Methods |  | 0:25 |  |  | Just look through the JSON files.
"alternatively, we can discuss…" - Topic sentence mismatch. Rewrite to match what is written below (where each parameter shows up in the plot). | Content | Methods |  | 0:45 | 0:00 | 2024-08-29 | Deleted it. Unncessary.
Do I need to combine the model description section with the sequential calibration section? | Organization | Methods |  | 1:00 | 0:00 | 2024-08-29 | I think it flows incredibly now.
Think about moving the sequential calibration procedure to the appendix or to combine it with the model description section. | Content | Methods | Yes | 0:45 | 0:00 | 2024-08-29 | See what Jacob thinks. I like it there.
Add a branched function to the H_cur function | Math | Methods |  | 0:15 | 0:05 | 2024-08-29 | Just google it.
Pull Bigelow's figure for the non-constant stress influence coefficients. Also think about how this works, because the model should capture some of these changes (quadratic with stress) | Content | Methods |  | 0:25 | 0:15 | 2024-08-29 | Maybe could just delete this part.
Trim the model/calibration deficencies paragraph(s). The calibration is pretty damn good. | Content | Methods |  | 0:25 | 0:10 | 2024-08-29 | It's a short paragraph.
Add a few sentences about why SMAs are used (high work energy density), specifically highlighting the actuator properties. | Content | Intro | Yes | 1:00 | 0:15 | 2024-08-15 | The less we spend on this, the better. Everyone has heard about the SMA "magic material" way too much.
Collect important references on model calibration tools (Abaqus/others?) | References | Intro |  | 2:00 | 0:45 | 2024-08-15 | Emailed the contact at Abaqus, will probably add one more citation, but it's done.
Collect citations on optimization for SMA model calibration | References | Intro |  | 0:30 | 0:10 | 2024-06-10 | Pedro/Whitten/Walgren/Bertagne
Percent Complete |  |  |  | 31.25%
Total Time Elapsed |  |  |  | 0.92014 | 0.010417

## Citations to add
Number | Section | Sentence | Notes
1
2