## First Draft
Task | Type | Section | Jacob Flag | Estimated Duration | Actual duration | Date of completion
Collect important references on model calibration tools (Abaqus/others?) | References | Intro |  | 2:00
Paragraphs describing the pre-processor (filtering/plotting/data selection) | Content | Methods | JACOB | 3:00
A few paragraphs on the post-processor. What do we do with the data? (We haven't really talked about this before). | Content | Methods | JACOB | 1:30
Set of figures describing the full manual calibration process. Strain-temperature (a), E^A (b), TTs and Cs ©, trans. Strain (d). Include alpha in (a) and ©. | Figure | Methods |  | 2:00 | 3:00 | 2024-05-14 | Got it drafted on paper. Move to inkscape now. Maybe play with the aspect ratios to get everything down.
Add a table with the two calibration parameters.
What is SMA constitutive model calibration? (paragraph) | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
Why is model calibration important? (paragraph) | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
What is the current state-of-the-art for model calibration? (paragraph) | Content | Intro |  | 2:00 | 0:15 |  | Word dump complete.
Any drawbacks to the current state-of-the-art? (paragraph) | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
Figure describing the full design process (property definition -> alloy development -> alloy fabrication <-> property determination -> model calibration -> design with component) and how our tool speeds this process up. | Figure | Intro | JACOB? | 3:00 | 2:30 |  | Mostly done. Just need to fine-tune it.
Figures justifying the need for numerical optimization. Pull from the SMASIS slide deck. | Figure | Intro |  | 1:00 | 1:30 | 2023-11-05 | I have a handful of figures, but probably need to clean these up and trim them down.
Flowchart describing the different components of the tool (pull from SMASIS slides). | Figure | Methods | JACOB | 1:30 | 1:00 |  | Mostly there. Just fine tuning.
Justify the use of the 1D Lagoudas SMA actuator model. (applicability to more complex systems, dearth of tools on that area, etc.) | Content | Methods |  | 1:00
Briefly describe the 1D Lagoudas SMA model (write out all the equations). Probably re-write it in terms of an elastic domain, yield critierion, and flow rule. | Content | Methods |  | 2:00
Describe optimization scheme (hybrid optimization) | Content | Methods |  | 1:00 | 0:45 | 2023-11-06 | Word dump complete.
3 paragraphs on conclusions (open source, speed of development, other applications) | Content | Conclusion |  | 1:00 | 0:15 | 2024-04-23 | Word dump complete.
2 paragraphs on further refinements (alternative loading modes, model formulations, anything else?) | Content | Conclusion |  | 1:00 | 0:05 | 2024-04-23 | Word dump complete.
Figure detailing difference between hybrid optimization, GA, and gradient-based methods. | Figure | Methods |  | 2:00 |  |  | Probably don't need this figure. It's not an optimization paper - it's a model calibration GUI paper.
Write the thesis statement paragraph | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
Collect 5-10 references on SMA model calibration | References | Intro |  | 2:00 | 1:50 | 2023-09-20
Collect the important references on existing open-source tools for SMAs (NASA). | References | Intro |  | 2:00 | 2:30 | 2023-09-23
Table of unknown parameters (design variables), their physical meanings, and SI units. | Table | Methods |  | 2:00 | 0:30 | 2023-10-03
Figure outlining calibration progress (4 subfigures showing convergence to the true solution?) | Figure | Example |  | 1:00 | 3:00 | 2024-02-27 | I have a table to go through this. Showing the analytical solution then moving to the optimized solution.
Percent Complete |  |  |  | 72.73%
Total Time Elapsed |  |  |  | 1899-12-31 11:00 | 0.75694

## Second Draft
Task | Type | Section | Talk to Jacob? | Estimated Duration | Actual duration | Date of completion | Notes
Should we change "preprocessing" to "processing" to take a less model-centric perspective? | Figures/Org | Intro | Yes | 0:25
Think about organization with figure 2 (SMA-REACT description). Does this belong in its own section? | Organization | Intro |  | 0:25
Methods -> 1D Constitutive Model: Is this section a primer on SMAs constitutive models, or on how you need numerical optimization for calibration? | Content | Methods |  | 0:30
Ask Jacob to see if we can get a preprint of the SMA book chapter on calibration. | Organization | Methods | Yes | 0:10
Get a citation for how to select the calibration stress | References | Methods |  | 0:15
Make the conventional/sequential calibration figures better aspect ratios. | Figures | Methods |  | 0:25
Add a sentence or two about our intended audience for the paper (we write this paper for…). That allows us to scope the mathematical details of the paper. | Content | Intro | Yes | 0:25 | 0:00 | 2024-08-30 | From that scoping, I'll know how much detail we'll need to provide on the Lagoudas constitutive model. Don't think we need this.
Clean up the "current tools" paragraph | Content | Intro |  | 1:00 | 1:00 | 2024-08-29
Paragraphs describing the pre-processor (filtering/plotting/data selection) | Content | Methods | Yes | 3:00 | 0 | 2024-08-15
A few paragraphs on the post-processor. What do we do with the data? (We haven't really talked about this before). | Content | Methods | Yes | 1:30 | 0 | 2024-08-30 | I just deleted it.
Consider deleting first paragraph in model calibration | Content | Methods |  | 0:45 | 0 | 2024-08-30 | Just read through to make sure it flows.
2nd paragraph in model calibration: Move the last sentence to be the topic sentence. | Content | Methods |  | 0:30 | 0 | 2024-08-30 | Make sure it flows and make sure I'm not saying the same thing twice.
Collect references on analytical calibration methods for SMAs | References | Methods |  | 0:45 | 0 | 2024-08-30
Model calibration, paragraph 5: Have I mentioned material property interdependence before now? | Content | Methods |  | 0:45 | 0 | 2024-08-30
Do I need to divide model parameters into free variables and specified quantities? | Content | Methods |  | 0:30 | 0
Get a citation for how in most cases the H_min and sigma_crit are zero. | References | Methods |  | 0:25 | 0 |  | Just look through the book or other examples. This makes sense, because you'll either get grain realignment or you won't…
The statement about how the ASTM standard defines properties in a different manner than the Lagoudas model is buried in a paragraph. Pull that out. | Content | Methods |  | 0:15 | 0 |  | Maybe move this up to a section about why we need a separate calibration tool.
"In past work,…" move this to a more relevant section. Maybe to the introduction? Maybe cut it in general? | Content | Methods |  | 0:20 | 0
Check the entire model description section for any mathematical rationale that doesn't have the accompanying math. | Content | Methods |  | 0:45 | 0
Change iterative calibration/conventional calibration to sequential? Because both are iterative. | Content | Methods | Yes | 0:30 | 0 |  | Figure out something that Jacob can understand.
Look through the ASTM standard to pull a quick discussion about what stress levels to pick out. | Content | Methods |  | 0:30 | 0:15 | 2024-08-30 | Keep it succint. This isn't an SMA characterization paper. Doesn't make any note of them.
Add the data for the bounds on the concurrent/global calibration section | Content | Methods |  | 0:25 | 0:15 | 2024-08-30 | Just look through the JSON files.
In the SMA development process, do we need to introduce roles and personas for each person doing a different stage of the work? | Content | Intro + Methods | Yes | 0:30 | 0:15 | 2024-08-29 | If we introduce different personas and decide on titles, that'll make explaining the model calibration part much easier. Nope.
"alternatively, we can discuss…" - Topic sentence mismatch. Rewrite to match what is written below (where each parameter shows up in the plot). | Content | Methods |  | 0:45 | 0:00 | 2024-08-29 | Deleted it. Unncessary.
Do I need to combine the model description section with the sequential calibration section? | Organization | Methods |  | 1:00 | 0:00 | 2024-08-29 | I think it flows incredibly now.
Think about moving the sequential calibration procedure to the appendix or to combine it with the model description section. | Content | Methods | Yes | 0:45 | 0:00 | 2024-08-29 | See what Jacob thinks. I like it there.
Add a branched function to the H_cur function | Math | Methods |  | 0:15 | 0:05 | 2024-08-29 | Just google it.
Pull Bigelow's figure for the non-constant stress influence coefficients. Also think about how this works, because the model should capture some of these changes (quadratic with stress) | Content | Methods |  | 0:25 | 0:15 | 2024-08-29 | Maybe could just delete this part.
Trim the model/calibration deficencies paragraph(s). The calibration is pretty damn good. | Content | Methods |  | 0:25 | 0:10 | 2024-08-29 | It's a short paragraph.
Add a few sentences about why SMAs are used (high work energy density), specifically highlighting the actuator properties. | Content | Intro | Yes | 1:00 | 0:15 | 2024-08-15 | The less we spend on this, the better. Everyone has heard about the SMA "magic material" way too much.
Collect important references on model calibration tools (Abaqus/others?) | References | Intro |  | 2:00 | 0:45 | 2024-08-15 | Emailed the contact at Abaqus, will probably add one more citation, but it's done.
Collect citations on optimization for SMA model calibration | References | Intro |  | 0:30 | 0:10 | 2024-06-10 | Pedro/Whitten/Walgren/Bertagne
Percent Complete |  |  |  | 81.25%
Total Time Elapsed |  |  |  | 0.92014 | 0

## Citations to add
Number | Section | Sentence | Notes
1
2