## First Draft
Task | Type | Section | Jacob Flag | Estimated Duration | Actual duration | Date of completion
Collect important references on model calibration tools (Abaqus/others?) | References | Intro |  | 2:00
Paragraphs describing the pre-processor (filtering/plotting/data selection) | Content | Methods | JACOB | 3:00
A few paragraphs on the post-processor. What do we do with the data? (We haven't really talked about this before). | Content | Methods | JACOB | 1:30
Set of figures describing the full manual calibration process. Strain-temperature (a), E^A (b), TTs and Cs ©, trans. Strain (d). Include alpha in (a) and ©. | Figure | Methods |  | 2:00
3 paragraphs on conclusions (open source, speed of development, other applications) | Content | Conclusion |  | 1:00
2 paragraphs on further refinements (alternative loading modes, model formulations, anything else?) | Content | Conclusion |  | 1:00
Add a table with the two calibration parameters.
What is SMA constitutive model calibration? (paragraph) | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
Why is model calibration important? (paragraph) | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
What is the current state-of-the-art for model calibration? (paragraph) | Content | Intro |  | 2:00 | 0:15 |  | Word dump complete.
Any drawbacks to the current state-of-the-art? (paragraph) | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
Figure describing the full design process (property definition -> alloy development -> alloy fabrication <-> property determination -> model calibration -> design with component) and how our tool speeds this process up. | Figure | Intro | JACOB? | 3:00 | 2:30 |  | Mostly done. Just need to fine-tune it.
Figures justifying the need for numerical optimization. Pull from the SMASIS slide deck. | Figure | Intro |  | 1:00 | 1:30 | 2023-11-05 | I have a handful of figures, but probably need to clean these up and trim them down.
Flowchart describing the different components of the tool (pull from SMASIS slides). | Figure | Methods | JACOB | 1:30 | 1:00 |  | Mostly there. Just fine tuning.
Justify the use of the 1D Lagoudas SMA actuator model. (applicability to more complex systems, dearth of tools on that area, etc.) | Content | Methods |  | 1:00
Briefly describe the 1D Lagoudas SMA model (write out all the equations). Probably re-write it in terms of an elastic domain, yield critierion, and flow rule. | Content | Methods |  | 2:00
Describe optimization scheme (hybrid optimization) | Content | Methods |  | 1:00 | 0:45 | 2023-11-06 | Word dump complete.
Figure detailing difference between hybrid optimization, GA, and gradient-based methods. | Figure | Methods |  | 2:00 |  |  | Probably don't need this figure. It's not an optimization paper - it's a model calibration GUI paper.
Write the thesis statement paragraph | Content | Intro |  | 1:00 | 0:15 |  | Word dump complete.
Collect 5-10 references on SMA model calibration | References | Intro |  | 2:00 | 1:50 | 2023-09-20
Collect the important references on existing open-source tools for SMAs (NASA). | References | Intro |  | 2:00 | 2:30 | 2023-09-23
Table of unknown parameters (design variables), their physical meanings, and SI units. | Table | Methods |  | 2:00 | 0:30 | 2023-10-03
Figure outlining calibration progress (4 subfigures showing convergence to the true solution?) | Figure | Example |  | 1:00 | 3:00 | 2024-02-27 | I have a table to go through this. Showing the analytical solution then moving to the optimized solution.
Percent Complete |  |  |  | 59.09%
Total Time Elapsed |  |  |  | 1899-12-31 11:00 | 0.61806

## Citations to add
Number | Section | Sentence | Notes
1
2